## Sheet1
Related User Story | Task Description | Initial Estimate | Amount Remaining After…
|  |  | Week 1 | Week 2 | Week 3 | Week 4
create class for unit | create the unit class with veribles for name type point value model count and wargear | 2 | 2
create class for faction list | create the faction list class which will have a list of units a title and a total points value | 1 | 1
testing the classes | Unit testing | 3 | 6
create a classs to store faction lists | create class to store created Faction lists | 1 | 0.5
Home page ui | create home page UI | 2 | 0 | 2
Faction list UI | Create UI for createing a faction list | 3 | 0 | 2 | 1
unit UI | Create UI for createing a unit | 3 | 0 | 1
delete unit | delete unit from list | 1 | 0 | 0.5
delete faction list | delete list | 1 | 0 | 0.5
| Estimate Totals | 17 | 9.5 | 6 | 1 | 0